## Sheet1
Sl No. | Deliverables | Weeks | [15 empty] | Status
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Proposal Approval | [16 empty] | Completed | bar: Weeks 1
2 | Literature Review | [16 empty] | Completed | bar: Weeks 1 to Weeks 2
3 | Dataset Finalization | [16 empty] | Ongoing | bar: Weeks 3 to Weeks 4
4 | Data Wrangling | [16 empty] | Ongoing | bar: Weeks 3 to Weeks 4
5 | Data Statistics Reporting | [16 empty] | Pending | bar: Weeks 4
6 | VAE Model Implementations | [16 empty] | Pending | bar: Weeks 5 to Weeks 7
7 | Implementation of Anomaly Scoring Function | [16 empty] | Pending | bar: Weeks 5 to Weeks 6
8 | Model Evalution | [16 empty] | Pending | bar: Weeks 5 to Weeks 8
9 | VAE Anomaly Detection Performance Report | [16 empty] | Pending | bar: Weeks 7 to Weeks 8
10 | Implementation of GAN Model | [16 empty] | Pending | bar: Weeks 9 to Weeks 11
11 | Model Evalution | [16 empty] | Pending | bar: Weeks 9 to Weeks 12
12 | GAN Performance Report | [16 empty] | Pending | bar: Weeks 11 to Weeks 12
13 | Synthetic Data Generation | [16 empty] | Pending | bar: Weeks 11 to Weeks 12
14 | ML Model Performance Report | [16 empty] | Pending | bar: Weeks 13 to Weeks 14
15 | Comprehensice Evaluation Report | [16 empty] | Pending | bar: Weeks 14 to Weeks 15
16 | Dissertation Finalization | [16 empty] | Pending | bar: Weeks 16
17 | Submission | [16 empty] | Pending | bar: Weeks 16